TITAN Meeting

Date: Tuesday May 29 2007 	Time: 13:00

Chairperson: Jens

RFQ:

| Mathew | - Missing in action |
| --- | --- |
| Ryan | - pulled out RFQ, re-wired, increased coupling capacitors - RF ~95% of driver capacity now (rather than 50%), but still switches poorly, ions will still come out. - After put back in, pump (500) failed. To be fixed here ~ $1200 |

MPET:

| Ryan | - turbo controller, iron cables done now - electron gun installed by end of next week? |
| --- | --- |
| Mel | - Vacuum commissioning - Clara done by Wednesday, so Roughings done by Friday |
| Vladmir | - wiring cables (1/3 of all wires done) - precision trap finish by tomorrow, rest of electrodes need 1 – 1 ½ day more - Next week, penning trap wired on platform - Right now, no cable tray ( better do cabling after trap in place) - Plan such that tray able to swing – can we do better than just cable ties? |
| Alexei (RFdriver) | - short term plan: simplified system ready by August - long term plan: only need additional amplifiers to expand system - working with another person on RF, pick up that project after he leaves in June - Vladmir wants Alexei to calibrate 8 electronic channels (takes ~1 day) |

EBIT:

| Christian | - last Tuesday, installed collector, small leak from copper casket being a bit too wide. Fixed, re-installed. Now pressure at 10-6, going down slowly still. - Tried align Quadruple Triplet w.r.t end of beamline => off - 2 solutions: 1. fix quadruple triplet to align w/ housing 2. use crooked alignment, align quadruple’s center to EBIT magnet. - upon washing, realized wing filter is steel. - difficult for outgassing, worried about rusting. |
| --- | --- |
| Alain | - install beam-line this week - fix alignment, then turn on EBIT - install power supply this week. - Next steps: tests with test ion source. |
| Thomas | - got code in C++ - in Geant: constructing the pips detector, got electrons flying thus far |
| Cecilia | - ordered MCPs with phosphor screen - hand sketched designs to be discussed with Cam |

Note: Jens will be away in Japan next week, Paul will chair the meeting.